## Sheet1
Description | Start Date | End Date | Status
Mobile Inventory -> Device Handover Form | 2024-04-25 | 2024-04-28 | Done
Sales Reports -> Daily Acheivement Summary (Item) Report | 2024-04-28 | 2024-04-30 | Done
Booking and Actual Module -> Stock Entry Form | 2024-05-06 | 2024-05-15 | Done
Sales Reports -> Daily Item Wise Sale | 2024-04-30 | 2024-04-30 | Done
Sales Report -> Agency Info ->Invoice Cancel | 2024-05-02 | 2024-05-02 | Done
Sales Report -> Agency Info -> Discount Daily Report | 2024-05-03 | 2024-05-03 | Done
Raigam SFA API -> Soya Price Survay | 2024-05-06 | 2024-05-09 | First Presentation
Booking and Actual Module -> Bill Entry | 2024-05-10 | 2024-05-15 | Done
Target Excel Upload | 2024-05-28
New Inventory Panel
Initial Setup | 2024-05-03 | 2024-05-03 | Done
User Related -> User Register | 2024-05-06 | 2024-05-06 | Done